## CLIN Summary
Frasier Digital, LLC — Price Proposal (Volume III, Factor 4)
Solicitation PANHEC-26-P-0000-026407 — CWMS Database Authorization Maintenance and Improvements
Firm-Fixed-Price per task CLIN · Period of performance 360 days from award · Options per RFO 52.217-7
CLIN | Task | Description | Qty | Unit | Price
1001 | Task 1a | Development meetings (26) | 1 | Job
2001 | Task 2 | Improve authorization web UI and CDA integration | 1 | Job
3001 | Task 3a | Implement authorization in CWBI-Dev | 1 | Job
5001 | Task 5a | Maintenance (≤803 h) | 1 | Job
1002 | Task 1b | Development meetings, additional 26 (option) | 1 | Job
3002 | Task 3b | Implement authorization in CWBI-Test (option) | 1 | Job
4001 | Task 4 | Load testing (option) | 1 | Job
5002 | Task 5b | Maintenance (≤704 h) (option) | 1 | Job
Base tasks subtotal (CLINs 1001, 2001, 3001, 5001)
Option tasks subtotal (CLINs 1002, 3002, 4001, 5002)
GRAND TOTAL — base and all options

## Labor Rates
Frasier Digital, LLC — Fully Burdened Labor Rates
Solicitation PANHEC-26-P-0000-026407 — CWMS Database Authorization Maintenance and Improvements
Person | Labor category | Key personnel | Fully burdened rate ($/hr)
J. Frasier | Project Manager | Yes | 165
S. Carpenter | System Engineer / Architect | Yes | 145
R. Daley | Senior Forms (React/TypeScript) Developer | Yes | 145
R. Chong | Senior Java Developer / Senior Oracle DBA (dual role) | Yes | 145
A. Frasier | Associate Software Engineer | No | 90
S. Chesky | Associate Software Engineer | No | 90

## Hours by Task
Level of Effort — hours per person per task (identical to Volume I, Factor 1, Table A-2)
CLIN | Task | Description | Option | J. Frasier | S. Carpenter | R. Daley | R. Chong | A. Frasier | S. Chesky | Total hours | Task price
1001 | Task 1a | Development meetings (26) | No | 78 | 12 | 12 | 20 | 0 | 8
2001 | Task 2 | Improve authorization web UI and CDA integration | No | 50 | 0 | 220 | 180 | 100 | 0
3001 | Task 3a | Implement authorization in CWBI-Dev | No | 40 | 120 | 0 | 40 | 0 | 0
5001 | Task 5a | Maintenance (≤803 h) | No | 70 | 0 | 100 | 210 | 0 | 400
1002 | Task 1b | Development meetings, additional 26 (option) | Yes | 78 | 12 | 12 | 20 | 0 | 8
3002 | Task 3b | Implement authorization in CWBI-Test (option) | Yes | 20 | 80 | 0 | 20 | 0 | 0
4001 | Task 4 | Load testing (option) | Yes | 20 | 60 | 0 | 60 | 0 | 40
5002 | Task 5b | Maintenance (≤704 h) (option) | Yes | 60 | 0 | 90 | 180 | 0 | 350
Total — base and all options